## Sheet1
Tasks | Start Date | End Date | Duration
Gather Requirements | 2nd feb 2017 | 2nd feb 2017 | 7
Dividing Roles | 3rd feb 2017 | 5th feb 2017 | 3
Meetings | 2nd feb 2017 | 16th feb 2017 | 4
Project planing | 3rd feb 2017 | 3rd feb 2017 | 7
Softwares | 10th feb 2017 | 18th feb 2017 | 10
Design Website | 10th feb 2017 | 19th feb 2017 | 10
App design | 15th feb 2017 | 19th feb 2017 | 10
Project WBS | 3rd feb 2017 | 12th feb 2017 | 3
Gantt Chart | 19th feb 2017 | 19th feb 2017 | 1
Logo | 11th feb 2017 | 12th feb 2017 | 2