## Sheet1
Tasks | Start Date | End Date | Duration
Dividing Roles | 2nd Feb 2017 | 2nd Feb 2017 | 1
Gathering requirement | 3rd Feb 2017 | 5th Feb 2017 | 3
Meetings | 2nd Feb 2017 | 16th Feb 2017 | 4
Project Planing | 3rd Feb 2017 | 10rd Feb 2017 | 7
Softwares | 10th Feb 2017 | 18th Feb 2017 | 10
Logo | 9th Feb 2017 | 13th Feb 2017 | 4
Project Name | 2th Feb 2017 | 5th Feb 2017 | 3
Colour Scheme | 9th Feb 2017 | 10th Feb 2017 | 1
Design Website | 10th Feb 2017 | 10th Mar 2017 | 30
App design | 15th Feb 2017 | 17th Mar 2017 | 30
Project WBS | 3rd Feb 2017 | 10th Feb 2017 | 3
Gantt Chart | 19th Feb 2017 | 19th Feb 2017 | 1